## Sheet1
Task	Orig. Est.	Curr. Est.	Effort	Remain	Responsible
Setup working envrironment	3h	3h	3h	0h	Fellinger
Menu/GUI	3h	4h	3h	1h	Haiden
Server to connect to	24h	n/a	0h	24h	Fellinger
Player(s) can move	12h	n/a	0h	n/a	n/a
Game logic	12h	n/a	0h	n/a	n/a
Lobby	10h	n/a	0h	n/a	n/a